## Slide 1
Progress report
Weekly Development
Progress Report
Presenter Maya Lin @Maya
Date October 9, 2026

## Slide 2
Executive Summary
This Week at a Glance
App Store Release
100%
Completed
Developer Account Verified
Apple approved our company account; the app is now in TestFlight.
ClinicBook · Patient & Clinic
65%
On track
4 of 8 Phases Complete
Patient app and clinic dashboard are being built in parallel.
PulseBoard Analytics
1 / 2
On track
Workstreams Complete
Data transfer to the new system finished; usage tracking is being rolled out.
Key update One decision is needed this week: can patients turn off SMS reminders and keep email only? (see Decisions Needed)

## Slide 3
Mobile · App Store Release
App Store: Developer Account Verified
Blocker resolved
!
Last week
Blocked
Waiting for the company's D-U-N-S business number.
✓
This week
Number Received
Operations provided the D-U-N-S number.
✓
This week
Account Verified
Apple verified the company developer account.
✓
This week
In TestFlight
First build available to internal testers.
Business Impact: The app is published under the company's own verified account, ready for beta testers.

## Slide 4
ClinicBook · Progress Overview
ClinicBook: Patient App & Clinic Dashboard Progress
Chart: 
| Complete | Remaining
Combined Progress | 65 | 35
65%
Combined Progress
Patient app + Clinic dashboard · 8 phases
Chart: 
| Complete | Remaining
Patient App | 60 | 40
60%
Patient App
Owner: Leo Park @Leo
Chart: 
| Complete | Remaining
Clinic Dashboard | 70 | 30
70%
Clinic Dashboard
Owner: Nina Rao @Nina
4
Phases Completed
2
Phases In Progress
2
Phases Not Started
Progress = average completion of each track's four phases.

## Slide 5
ClinicBook · Phase Breakdown
ClinicBook: Status of Each Phase
Patient App
Dev: Leo Park @Leo
Chart: 
| P1 · Accounts & Sign-in | P2 · Clinic Search & Maps | P3 · Booking Calendar | P4 · Payments & Receipts (Not started)
Completed | 100 | 100 | 0 | 0
In Progress | 0 | 0 | 40 | 0
Booking calendar underway; payments are next.
Clinic Dashboard
Dev: Nina Rao @Nina
Chart: 
| P1 · Clinic Onboarding | P2 · Doctor Schedules | P3 · Reports & Exports (Not started) | P4 · Reminders & Notifications
Completed | 100 | 100 | 0 | 0
In Progress | 0 | 0 | 0 | 80
Reminders are in final review; 4 of 5 parts verified.

## Slide 6
ClinicBook · Patient App
ClinicBook: What Was Done on Each Task
In progress
P3 · Booking Calendar
Owner: Leo Park @Leo
Patients pick a doctor, a day and a time slot in one screen. Free slots update as other patients book, so nobody is offered a time that is already taken.
Details
Doctor and day picker built
Free time slots shown live
Booking confirmation screen
Rescheduling an existing booking
Cancellation with clinic notice
Completed
P2 · Clinic Search and Maps
Owner: Leo Park @Leo
Patients find nearby clinics by name, specialty or distance and open directions in their maps app. Reviewed and approved this week.
Details
Search by name and specialty
Distance sorting from the patient's location
Directions open in the maps app
Works offline for recent searches
Not started
P4 · Payments and Receipts
Owner: Leo Park @Leo
Patients pay the booking deposit in the app and get a receipt by email. Starts after the booking calendar is approved.
Details
Choose a payment method
Pay the booking deposit
Receipt sent by email
Status as of this week's review; detail comes from the task tracker and the lead's code reviews.

## Slide 7
Quality · Code Review
Quality Check: Issues Caught Before Release
3
Features reviewed this week
2
Approved for release
212
Automated tests passing (100%)
Appointment Reminders
Clinics can send SMS and email reminders 24 hours and 2 hours before each appointment.
Verified
Reliability
A patient could receive the same reminder twice if sending is retried. Small fix identified.
Fix before release
Privacy
Patient phone numbers are hidden in system logs and only visible to clinic staff.
Verified
Source: lead's code reviews this week.

## Slide 8
Needs Attention
Blockers & Decisions Needed
Blockers & Risks
!
Reminders release waiting on one fix
Duplicate reminders must be prevented before release. Fix is small and already tested.
Owner: Nina Rao @Nina · Expected: next week
Decisions Needed
?
Can patients turn off SMS reminders and keep email only?
Today every patient with a phone number receives SMS reminders; some clinics report complaints.
Options: allow opt-out · clinic decides per patient · keep as today

## Slide 9
Team · Task Tracker
Developer Task Track
Leo Park @Leo
ClinicBook · Patient App
3
done this
week
2
open
60%
Sign-in and clinic search done; booking calendar in progress.
P1 · Accounts & Sign-in (3/3)
P2 · Clinic Search & Maps (5/5)
P3 · Booking Calendar (2/5)
P4 · Payments & Receipts (0/4)
Nina Rao @Nina
ClinicBook · Clinic Dashboard
4
done this
week
1
open
70%
Onboarding and schedules done; reminders in final review.
P1 · Clinic Onboarding (3/3)
P2 · Doctor Schedules (5/5)
P4 · Reminders, in review (5/5)
P3 · Reports & Exports (0/3)
Maya Lin @Maya
PulseBoard · Analytics
5
done this
week
1
open
75%
Data transfer done; usage tracking rolling out.
Data transfer to new system
Event plan agreed
Usage tracking rollout
Code reviews, 3 features
Done/Open = planned tasks this week; work in review stays open until approved.

## Slide 10
Engineering Activity · GitHub
Team Delivery Activity This Week
Chart: 
| Leo Park @Leo | Nina Rao @Nina | Maya Lin @Maya
Development work | 18 | 14 | 6
Features submitted | 1 | 2 | 1
Features approved | 2 | 1 | 1
Reviews given | 0 | 3 | 4
Source: GitHub activity this week.
3
Features approved
2
In final review
7
Code reviews completed

## Slide 11
Looking Ahead
Next Week's Plan
Project / track | Owner | Next focus | Current
ClinicBook · Patient App | Leo Park @Leo | Finish the booking calendar, then start payments and receipts. | P3 · 40%
ClinicBook · Clinic Dashboard | Nina Rao @Nina | Apply the duplicate-reminder fix and release reminders; start reports and exports. | P4 · 80%
PulseBoard · Usage Tracking | Maya Lin @Maya | Finish adding usage tracking to the web app, then open the first dashboard to managers. | IN PROGRESS
App Store Release | Maya Lin @Maya | Invite the first 20 clinic staff to TestFlight. | NOT STARTED

## Slide 12
Thank you
Questions & discussion
Presenter Maya Lin
Date October 9, 2026